>>  PROGRESS / FINAL REPORT  <<

When you receive a grant from the Surdna Foundation, we ask that you please provide periodic updates about your work so that we may understand progress toward our shared goals.  We’re particularly interested in learning about what helps you to succeed and what, if any, challenges you encounter during the grant period.  Please know we value your experience and encourage your openness and candor.

Our grant application requests information about key goals, activities planned, and anticipated results; through the attached reporting document, we loop back to that information and inquire about your progress.  Please check out the questions we pose in this document, and incorporate your answers to these questions into your progress and final reports.

You may send your report to us as a Word file via email to kmusler@surdna.org.  If you cannot send your report electronically, you may opt to send it via regular mail to:

- Kim Musler, Program Associate for the Nonprofit Sector

Surdna Foundation

330 Madison Avenue, 30th Floor

New York, NY  10017

Please feel free to contact Surdna program staff should you have any questions about this process.  If you have technical questions about submitting a grant report, you may contact us by e-mail at jgoldberg@surdna.org  Please type Reporting Questions in the subject line.

>>  SECTION 1:   FINANCIALS AND CERTIFICATION <<

NOTE:  This section must be completed and signed by an officer of your organization (e.g., CEO, President, Executive Director, COO CFO, Comptroller, or Treasurer).

Organization Name: The Media Consortium

Date: 2/20/8

Grant Number: 20080420

Grant Amount and Duration: $100,000 from 2008-2009

Any Special Conditions (e.g., matching terms): None

Purpose of Grant: General Operating Support for The Media Consortium and its projects

Amount of grant funds remaining as of this date: $0.00

Please attach:

- A schedule detailing the income and expenditures made in reference to the grant (i.e., how Surdna funds were expended), including salaries, travel, supplies and other pertinent expenses.

All expenditures detailed here have been made in accordance with the stated purpose of the grant.  I hereby certify on behalf of this organization that I have examined the information provided in this report and to the best of my knowledge it is true, correct and complete.  I further agree to notify the Surdna Foundation immediately if any of this information changes.

____________			Tracy Van Slyke, Program Director_

Signature					Name and title

[typing name here constitutes electronic signature]

>>  SECTION 2:  PROGRESS / FINAL REPORT <<

NOTE:  If this grant was for general operating support, please use these questions as a guide for reporting on the primary objectives of your organization’s work.

- WHAT DID YOUR ORGANIZATION DO DURING THE GRANT PERIOD?

The Media Consortium is the leading space for independent media and its allies to strategize, collaborate, and launch projects that are transforming the independent media sector. Our core goals are to amplify independent journalism's voice in broader public debates, invest in core infrastructure opportunities and improve coordination and collaboration among our partners and allies.

Our 2007 proposal to the Surdna Foundation outlined the following areas of focus and projects in 2008: Network Coordination, Infrastructure Building and Amplifying Our Collective Voice.

Network Coordination

Every year, The Media Consortium convenes two in-person meetings for our members and allies. In May 2008, more than 65 members, friends, and allies converged in Denver, Colorado for The Media Consortium's eighth membership meeting. The two-day meeting focused on bringing ideas into action.

Consortium staff debuted several key projects including Live From Main Street, the MediaWire project, and the Online Advertising Network during the Denver meeting. [More on these projects below.] In the form of member-organized "Media Labs," small groups were provided in-depth peer-to-peer assistance in sessions focused on Web 2.0, advertising and marketing. MC members also met with local organizations and advocates in order to get story tips and logistical information in advance of the Democratic National Convention, which took place in Denver only a few months later.

During the meeting The Media Consortium’s Project Director Tracy Van Slyke and strategic consultant Tony Deifell, president of Next Consulting, led two large-scale brainstorming sessions focused on the future of the independent media landscape. The results from these brainstorming groups were integrated into the consortium’s strategic process throughout 2008.

In July, The Media Consortium's Coordinating Committee came together for a two-day strategy retreat in New York. The meeting focused on two action items: informing our Game Changers strategy project (see more below). The coordinating committee and consortium staff also reflected on the previous year of the organization and laid the groundwork for a consistent 18-month strategy.   Overall, they developed four strategic principles for Media Consortium initiatives and projects in 2009-10, including:

- Build and Diversify the Media Leadership Pipeline

- Bring Money into the Sector

- Foster Collaboration among MC members and like-minded organizations

- Focus on Audience Development through demographic research and strategic outreach.

These principles were developed in response to the successes and lessons learned from previous projects, the needs of the sector, and by analyzing how The Media Consortium can build the impact and sustainability of independent media, especially during these critical times.

Tying the outcomes of these meetings as well as future planning together, Van Slyke and strategic consultant Tony Deifell, have worked to craft the network’s strategic research to look at not just the year ahead, but understand what the future holds for independent media two to eight years in the future and how the independent media can lead in this space.  The focus of this research centers on the creation and implementation of "Game Changers,” which we define as:

Developments (projects, initiatives, strategies, new models, innovations) that "change the game" for independent media by increasing its impact and influence in the next five years. By definition, these aren't incremental strategies, but rather big bold moves that the MC could develop or take advantage of in a rapidly changing media landscape.

Throughout 2008, Van Slyke and Deifell created a process to unearth, identify and synthesize current and future shifts in the media landscape and their implications for independent media. The team has outlined different possible scenarios for the future of media and politics, interviewed many MC members and dozens of experts in the fields of media, technology, politics, and business. These interviews provided perspective on current opportunities, challenges and uncertainties for the sector as well as new possibilities for The Media Consortium and its members to adapt significantly impact and change the landscape.

A final report on this project is due in March 2009, but preliminary findings were released at our February 2009 meeting in DC. Please contact MC staff for more background information on this exciting project.

Infrastructure Building

In our 2007 proposal, the consortium wrote that it was focusing on “building a Co-op database (housed by a third-party) that totaled audience numbers and demographic information from participating members. This database allows us to identify the scope and strength of our current audiences, initiate projects that bring in new sources of revenue for the sector, and develop collaborative marketing opportunities.”

In early 2008, Media Consortium staff began working with Dunn Data Co. to build upon our demographic research from 2006 and create a co-operative list that compiled audience numbers and demographic information from participating members. Ideally, the database would have allowed us to identify the scope and strength of our current audiences, initiate projects that bring in new sources of revenue for the sector, and develop collaborative marketing opportunities.

However, Dunn Data Co. went into bankruptcy not long after this project began. They became unable to provide MC staff with the necessary reporting or sales support to make this a successful project. TMC staff is now approaching this project from a different angle by working with Catalist, as outlined under the next bullet point of this report.

However, the initial findings from the co-op database project planted the seeds for a member-organized online Vertical Advertising Network-an opportunity to bring new revenue sources into the sector. In February, The Media Consortium hired the consulting firm Marketechnique to explore opportunities in building an online ad network for independent media outlets. Marketechnique and Media Consortium staff interviewed 10 members around their current advertising platforms, needs, and revenue opportunities. The Media Consortium also conducted a survey of the entire network, assessing the interest and viability of forming an online advertising network. Results included:

- 26 organizations have a total of 4,549,753 unique visitors and 55,776,186 page views per month.

- 24 organizations have email products that go out around once a week, reaching approximately 1,002,671 names. Of those 26 respondents, 12 offer ads on their email products.

- 12 respondents currently offer ads on their websites and three to four are interested in incorporating them.

During this time, Marketechnique surveyed the larger online advertising space and evaluated both the viability of a Media Consortium ad network and what would be needed to build it. Marketechnique created a report around the current online advertising sector and implications for Media Consortium members. Armed with this information, we determined that there was a significant opportunity for The Media Consortium to help members move into the online advertising network space. Consortium members AlterNet, Air America, Mother Jones and The Nation came together as the founding outlets for an independent media-focused ad network.

The member-founded ad network, now called Ad Progress, will debut in March 2009. Ad Progress will function as an “owner operated” online sales network for MC members and promises to provide additional revenue at lower costs than traditional ad network structures. This was a great milestone for The Media Consortium as we empowered members to lead a project that benefits the whole, not just one organization.

Amplifying Our Collective Voice

2008 has fostered a number of editorial collaborations and cooperative efforts to support amplifying the voice and impact of consortium members.  The Syndicated Reporting Project was started in 2007 to help fill coverage gaps for members and test if media outlets would share stories to create a larger echo chamber. In July 2007, The Media Consortium hired reporter Brian Beutler as its Washington Correspondent to cover Congressional Oversight and National Security and brought on Adele M. Stan as Executive Editor in early 2008.

Thanks to RSS and hyperlink technology, as well as to Brian's reputation within Washington D.C.'s blogging community, the articles moved from members' sites to the larger public. Beutler and Stan's stories were published by seven Consortium member organizations, including AlterNet, ColorLines, In These Times, Mother Jones, The American Prospect, The Progressive, and the Women's Media Center. In addition, their reporting has been linked and quoted by a number of blogs and websites including Slate, The Atlantic Online, Care 2, Common Dreams and the Huffington Post.

Based on feedback from July’s strategic planning meeting, the Syndicated Reporting project temporarily closed up shop at the end of September for a re-launch as a part of the MediaWires project in 2009.

A large part of The Media Consortium’s mission is to leverage the resources and journalism of its members to impact political discourse and debate. We want to showcase the first-rate independent journalism produced by MC members, move it to new and targeted audiences, and build the influence of independent media. With this goal in mind, we are harnessing new technologies, social networking applications and distribution opportunities to a launch the first phase of a MediaWire system that will allow members to share content, increase web traffic, and reach new audiences.

The Media Consortium has partnered with CommonSense New Media to launch its MediaWires project using Common Sense’s existing NewsLadder platform. Newsladder.net is the online aggregation spot to find TMC member content organized and archived by issue. This online platform offers a one-stop shop for the best in independent media, organized by specific topics. The Media Consortium is currently sponsoring three NewsLadders:

- Economy: http://economy.newsladder.net/

- Immigration: http://immigration.newsladder.net/

- Healthcare: http://healthcare.newsladder.net/

Along with these “one-stop shops” for the latest reporting on these issues, we have built out new ways to brand and build the audiences of Media Consortium members to increase their impact on the public dialogue. We are using new media tools including widgets, Facebook groups, RSS feeds, twitter alerts, online advertising and more to push our members’ journalism and expertise to new audiences.

We are also creating weekly blogs that round up and provide context to the "best of/most interesting" journalism produced by MC members throughout the week on the three topic areas. The blogs can be found at www.themediaconsortium.org/consortium-report/. They are available to all MC members, delivered to partners like the National Council for Research on Women and Young People For and posted throughout the blogosphere on sites including Firedoglake, Huffington Post, Open Salon, and more.

The Media Consortium is actively working to partner with non-profits, NGOs and other news organizations to feature the widgets, RSS feeds, and blog posts to promote, brand and raise traffic for its members. These partnerships are ideal for distribution because they effectively funnel reporting on specific topics to audiences that are already looking for more information about the topic. For example, by working with the Student-Farmworker Alliance, we are able to push content to their highly engaged constituency. SFA also benefits by being able to present itself as a resource to its audience.

Last, but not least, The Media Consortium produced Live From Main Street, a five-month town hall tour of the U.S. in election year 2008, hosted by GRITtv’s Laura Flanders. This production provided multiple opportunities for MC members to collaborate, share content and ultimately reached an audience of over 9 million people. Each town hall in this series focused on a key national issue through a local lens. The town halls were broadcast on dozens of radio stations, viewed on television channels such as Link TV and Free Speech TV and written about in print and online outlets.  Live From Main Street was produced by The Media Consortium, but had a separate budget and fundraising affiliation from the consortium itself.  The Media Consortium put $60,000 into Live From Main Street, along with significant staff time into supporting the development and promotion of the series and related content.

LFMS finished its run in October after five successful town halls in Minneapolis, Miami, Denver, Columbus and Seattle. Each event provided unique opportunities for local and national partnership, collaboration, and movement strategizing. Clips from all of the Live From Main Street town halls can be found at www.livefrommainstreet.org or youtube.com/livefrommainstreet.

Materials from the town halls were available for open source distribution among Media Consortium members, allies and partners to virally disseminate around the Internet for maximum impact. Members of The Media Consortium also collaborated to produce original content connected to the issues of each town hall. Live from Main Street also partnered with national outlets and groups including MoveOn.org, Free Press, FireDogLake, and many others to publicize and disseminate this content. Local groups and partnerships ranged from Progress Ohio to the Miami Worker’s Center.

Many attendees contacted us, excited that independent media was paying attention to the issues and people that mainstream media has ignored. Live from Main Street’s town halls have been covered in local radio interviews, newspaper articles and blogs. We successfully propelled vital issues to new levels of media and public awareness.  We also raised awareness of independent media to a new group of organizations and individuals through the town halls, videos, reporting and more.

- Did the specific actions you took/activities you pursued during the grant period differ from what was originally proposed? Please reply yes or no… and if yes, why?  Describe the revised activities and the reason for the change.

Network Coordination
MC Meetings: Yes. Due to the elections and the packed news cycle at the end of the year, we did not hold a second all member meeting in 2008. MC staff instead focused on having a smaller strategy meeting in July with the coordinating committee.  This allowed us to focus on current projects and member participation throughout the year. We also began planning for an all-member meeting in early 2009, and redirected 2008 meeting funds to provide travel “scholarships” to members who needed extra assistance to make it to the meeting. It was vitally important to get as many members in the room as possible to begin planning the next evolution of the sector, and we wanted to make sure there was plenty of support to get them there.

Infrastructure Building

Yes. The Co-op database project did not progress in expected ways due to Dunn Data Co.’s bankruptcy. We did, however, use the information generated about our collective audience as a starting point for an online advertising network that is owned and operated by MC members. In addition, MC staff is currently in discussions with Catalist, a company which houses a database with over 250 million voter-aged individuals, making it one of the most comprehensive and largest database files the country. Catalist representatives are currently working with a small group of Media Consortium members to provide them with information on how independent media outlets could use their database to reach and target new audiences.  The Media Consortium and its members will take this information and decide if and how to expand its relationship with Catalist in the near future.

Editorial Collaborations

Yes and No. While the Syndicated Reporting project was a successful enterprise, we realized that editorial collaboration needed to have a more focused approach in order to maximize member benefit.  Based on the strategic principles outlined at the July Coordinating Committee meeting, we refocused the minimal original content that The Media Consortium provides to leverage, promote and drive traffic to Media Consortium members.

The MediaWires project is the newest direction for collaboration, connection and building out the audience for the sector. In 2009, we hope to spur multi-media collaborations and continue to build out partnerships with like-minded organizations to build the brand, traffic and audiences out of MC member content.

Live From Main Street had amazing success, and we learned critical lessons. (If interested, a more complete report on Live From Main Street is available for review.) Lessons learned from all our collaborations is helping to shape the development of 2009/2010 high-impact collaborations organized and developed by MC members and supported by The Media Consortium.

- Will you need to further adjust your originally proposed activities going forward, for the remaining grant period?  Please reply yes or no… and if yes, please describe.

Grant period is complete.

2.   DID YOUR ACTIVITIES HELP YOU TO MAKE PROGRESS TOWARD YOUR OVERALL GOALS?

Your proposal outlined intended short-term results (during the grant period) and long-term outcomes (beyond the grant period):

- Would you describe your overall progress toward achieving the outcomes described in your proposal as: __significant    - or -  __mixed/modest   - or - __minimal?

The Media Consortium made significant progress towards achieving the outcomes described in our previous proposal.

- Please describe why, including specific examples.

The Media Consortium experienced extraordinary growth in 2008. We launched four dynamic projects, shored up organizational infrastructure, and began articulating a vigorous future for independent media. In 2007, The Media Consortium had two part-time staff and had started two projects. Today, we have two full-time and four part-time, project-based contractors, and almost 50 organizational members. We have also developed and fine-tuned the purpose, mission and strategy of The Media Consortium as a movement-building and sector-strengthening organization.

In a time of dramatic economic instability and tremendous change for the overall media sector, we are creating a space to not only ask tough questions, but to create concrete solutions that benefit many organizations. The projects we undertook in 2008 allowed us to diagnose the needs of the sector and implement projects in areas related to audience, infrastructure and collaboration.

3.  WHAT IS YOUR CORE / KEY FINDING?

The media sector is in a severe crisis. The changing technology landscape and advent of online tools were already significantly shifting business models, content production and audience development for our members. The economic crisis has accelerated this process and made the need for innovative projects and strategy crucial to the survival of independent media.

Over the past year, we learned that there is a definitive need and opportunity for the kinds of programming and strategic thinking that The Media Consortium supports. The Media Consortium’s big breakthrough came during our July 2008 strategy meeting, when the Coordinating Committee and Media Consortium staff developed four strategic principles to guide the growth and define the role the organization plays for its members.

These principles are:

- Build and Diversify the Media Leadership Pipeline

- Bring Money into the Sector

- Foster Collaboration among MC members and like-minded organizations

- Focus on Audience Development through demographic research and strategic outreach.

The development of these strategic principles was a key moment for the Consortium’s ability to evaluate current projects and plan for the future. It is clear that the need for such infrastructure and strategic support is only going to continue to grow as the media and economy continue to shift. On a capacity level, the Consortium must remain focused on aiding the sector to implement strategic and long-tem initiatives that concretely benefit our members.  But we also need to be nimble enough to respond to the ever-more frequent policy, economic and technological crisis and opportunity moments that fundamentally impact our members.  This puts a strain on our small staff and makes it difficult to allocate resources. It is an issue we must deal with in 2009.

4.  HOW DO YOU KNOW HOW YOU’RE DOING?

Your proposal identified certain measures or indicators that would be used to chart your progress during the grant term.  Please tell us what you’re finding as you review these (or other) measures or indicators:

- What specific evidence do you have of progress during this grant term?

Speaking purely in numbers, the Media Consortium’s membership body and scope of projects have grown substantially in 2008. We’ve gone from testing a few projects that encouraged relationship building and collaboration (like the early phases of the syndicated reporting project and the co-op database) to developing long-term projects that will benefit the individual members and the independent media sector as a whole.

When the consortium first formed, members were wary of sharing information and working together. Today, they are developing collaborative projects on their own because The Media Consortium provided the space for developing deep professional relationships. Overall, the Consortium is providing the space for independent media to collectively strategize for a dynamic future. Our work is ensuring growth and unity within the sector, rather than the fracturing and folding that is facing mainstream and traditional media outlets.

Combined with our guiding principles, projects like the MediaWires, the fostering of Ad Progress, and the Game Changer strategy report, as well as additional projects planned for 2009, are laying the groundwork to lead this sector forward—and prevent the financial and technical stagnation facing traditional media.

One of the big measures for our success over the next 12 months is to see how our projects will be fulfilling our four strategic principles. These principles are the guiding paths to internal evaluations, but also provide a framework for action steps and future developments.

- What is the most important, key measure that your organization tracks over time?  (Your response here may differ from your response above, and may even be unrelated to this grant.)

Above all else, we track the potential and actual benefits of MC-sponsored projects for our members and the sector as a whole. We ask the question, “How are members benefiting?”  There are three sub-areas we examine.

- Sustainability: Are we supporting efforts that bring in new money or relieve financial burdens for members? Are we setting the stage for long-term sustainability for the sector?

- Impact: Is the projects supporting its members to have more of an impact on the public and political debate? Is the project helping to build connections among members as well as outside partners to increase impact?

- Audience: Is the project helping members and their journalism reach and build its audiences now or in the future?

- What constraints, if any, are there on your organization’s ability to chart, monitor and understand its own progress over time?

The Media Consortium provides space and resources for independent media outlets to think big and beyond quick fixes. Our projects are focused on concrete gains for our members.  At the same time, we are dealing with media organizations that are already economically pinched and an overall media system that is in an apocalyptic moment. As a result, some of our projects do not have immediate results, but require a combination long-term planning and nimble flexibility to make sure that they reach their full potential.  We have made remarkable strides in 2008 for such a young network, but some of our newer projects might not have concrete, measurable results until mid-2009.

If this is a final report, please also tell us:

5.   WHAT IMPACT DO YOU THINK THE WORK SUPPORTED BY THIS GRANT HAS HAD?

- What you have learned about what works?  For example, has your work:

Created a new approach for your community or constituents?

Informed the work of other professionals or organizations?

Contributed to a change in policy - or mindset?

Strengthened an institution so that it is better able to fulfill its mission?

We’ve learned that there is a definite need and concrete benefit to Media Consortium projects, collaborations and strategic initiatives. Many mainstream and independent media organizations are shrinking and dying due to economic and technological stresses. The Media Consortium has created a space for members to think broadly about the purpose, impact and potential for their work. By investing in projects that benefit our members, we are relieving day to day operational stresses for these institutions. We’re also providing stable ground to test projects and initiatives that will have a maximum benefit for the sector for years to come.

While a change in national media policy has yet to come, we have seen a dramatic shift in the internal policies/mindsets of individual member organizations. Members are comfortable working together to share ideas and collaborate around projects. They are confident about the internal benefits to this kind of work—so much so that many have begun collaborating outside of MC supported projects.

- What lessons does your work have for other similar efforts?

What would you suggest other grantees - or other funders - attempt and/or avoid?

Developing a network of organizations with very different internal agendas and comfort levels can be difficult at first, but by taking incremental steps, there can be huge benefits for the sector. The Media Consortium has invested a great deal into developing one-on-one relationships with our members as well as supporting and connecting our members with each other. This groundwork helped create the partnerships necessary for critical big-picture thinking about the survival of this sector. Our first recommendation to any organization hoping to achieve similar levels of success is to build person-to-person relationships with members and help those members build those relationships among themselves. These relationships are key to the development of a lasting infrastructure—and to creating dynamic projects that benefit many different types of organizations.