August 16, 2012

Minutes

Present: Jo Ellen, Linda, Eric, Lisa, Steve, Rinku,, Alan

Absent: Jason, Cindy [medical issue with husband], Maya [on honeymoon]

Check-in

1) Financial/Development Report—Next Steps

Jo Ellen:

1) close the loop with Yolanda/Helen to release $$ from MPREP

2) Calculate exposure for FNP if TMC is at zero cash on Dec 31 and needs to shut down.

3) Plan a panel or series of panels at NCMR

Rinku:

Organize first meeting of the Decision Point CC Subcommittee. Members include:

Rinku, Jo Ellen, Steve, Eric

Lisa R and Jo Ellen

Recruit members for a TMC Development Committee and organize first meeting.

2) Annual Meeting: February 6-8, Baltimore

We will announce a hold the date for the annual meeting, as it can happen whether TMC is a funded organization or not.

3) Next Meeting

Our next regularly scheduled meeting is Thursday, September 6  at 1pm ET. There are some conflicts at this time, so the meeting may be moved. Please send me information on when you are available between September 4-14.

I. Financial and Development Report

PLEASE TAKE SOME TIME TO REALLY READ THE ATTACHED Q2 P&L AND THE REVISED BUDGET I HAVE CREATED, SHOWING ACTUALS.

| Grants—In Hand | Amount | Restricted? | Notes |
| --- | --- | --- | --- |
| Wallace Global | $30,000 | No | $28,900 to salary/expenses |
| MDF | $30,000 | Yes | $12,900 to salary/expenses |
| Harnisch | $10,000 | Yes | 100% to matching grants, none to TMC |
| Metrics, various | $25,000 | Yes | $2,250K to salary in 2012 |
| Grants--Expected |  |  |  |
| Gill Foundation | 21,500 | Yes | $3,250 to salary/expenses; delayed due to delay at funding partner AINN |
| Grants—In Process |  |  |  |
| Grants—In Potentia |  |  |  |
| Park Foundation | $175,000 | Yes | $21,000 to salary/overhead =fracking collab |
| 11th Hour | $175,000 | Yes | $21,000 to salary/overhead=fracking collab |
| Total Expected/In Hand | $116,500 |  | $47,300 to TMC salary/overhead |

External Revenue--Expected

| Type | Amount | Notes |
| --- | --- | --- |
| Membership Dues | $23,675 |  |
| Fundraiser | $2584 | In Hand |
| Sponsorships | $2500 | Truthout for Fundraiser—In Hand |
| Lab Fees | 990 | Long Form Journalsim |
| Total | $29,749 |  |

TOTAL Revenue Raised in 2012 for salary/expenses (excludes member regrants): $77,049

Total Expenses Expected in 2012: $95,222

1. TMC 2012 budget revised August 2012
I have recast the 2012 budget yet again, based on my conversation with Schwartz.

2. TMC cash on hand
Cash on hand now once again looks dire. I think we are looking at shutdown in October if we can’t get cash from any other source. October, we would be looking at a shutdown or at least a devolution of activities.

$54,000  on June 1

-$7000 burn rate per month

$33,000 est on Sept 1

+25,000 Schwartz first installment

+  4,000 in outstanding member dues

$62,000 in bank on Sept 1

-13,000 in restricted MPREP

-22,750 in restricted Schwartz

$26,000 in bank on Sept 1, unrestricted

Burn rate of 7,000 = 3+ months

3. The biggest problem is that I don’t have any funders I can turn towards to help out. The funding relationships TMC had started with in 2006-2009 became very unstable as the recession kicked in, with many of these funders changing their direction.  No new funders in media have arisen. TMC has only recently begun cultivating individual donors. We need one year of a significant capacity grant ($50-$100k) to get our external revenue plans in gear. Without that, it will be hard to move forward.

V. TMC Membership Report

The Membership Committee met June 5 and approved two new members: News Taco and Public Eye

|  | Dec 2011 | July 2012 |  Dec 2011-present |
| --- | --- | --- | --- |
| Starting # | 55 | 61 |  |
| New Members | 3 | 2 | 5 |
| Dropped Members | * | 3 | * |
| Total Members | 58 | 60 | 2 |

| Dropped Members | Number | Detail |
| --- | --- | --- |
| Nonpayment of Dues | * | 2 members did not pay 2011 dues, Democracy Now, Worker’s Independent. |
| Out of Business | 1 | GritTV |
| Other | 2 | Change.org and media venture collective are no longer doing any original journalism. They remain “friends” of TMC but not members. |

We are now collecting 2012 dues. As of June 15, 28 had paid dues and 32 had not paid dues. I have made an arrangement with New America Media. NAM has given me storage space for TMC files and materials, and use of a desk for interns, for free, in exchange for membership.

The membership committee has concerns about the size of TMC and our criteria for admitting new members. As a result, they put Shelterforce and Vancouver Observer on hold in March. We plan to discuss this at a meeting in July/August.

Membership Committee Members are:

Hanaa Rifaaey, AINN

Liz DiNovella, The Progressive

Jamia Wilson, The Women’s Media Center

Andrew Stelzer, Making Contact

Brian Stewart, Campus Progress

Shay Totten, Communications Director, Chelsea Green

VI. Project Report: Support and Innovation Projects

Metrics Incubation and Innovation Lab

The Metrics lab has begun in “stealth” mode. Prof Gary King has received his first funding round, and is currently hiring graduate students and setting up his lab. TMC is in negotiations to receive our first payment September 1; we are asking for a release of $10,000 for project management from September 1-January 1.

We anticipate the lab will begin to recruit TMC members in December, maybe sooner.

Long Form Journalism Lab

The long form journalism lab has launched!

How It Works Webinar Series

August—Localore?

September 5—Donor Development with Peter from Mother Jones

October—Advanced Google Analytics with Susan Mernit from Oakland Local

Project Report: Editorial Collaboration

Media Policy Reporting and Education Project

Briefings (open to all members)

March 7: Broadcast Disclosure Rules with Corie Wright and Andrew Schwartzman

March 29: Wireless Duopoly? With Parul Desai and Edyael Casaperalta

April 11: Why New LPFM Spectrum Matters with Brandy Doyle

April : SOPA Followup with Rebecca Jeschke and Josh Levy

May 7: Prison Phone Monopolies with amalia deloney and Lee Petro

July 2: Declaration of Internet Freedom with Josh Levy et al

July 25: Tiered Broadband

August 15: What the Government Knows About Your Data

Participants: Truthout, Oakland Local, Public News Service, In These Times, FSRN

Feature stories to date: 17

Possible Business Reporting and Education Project

Still an open possibility with ASBC, if we can find a funder. Proposal is ready.

Possible Labor Reporting and Education Project

In talks with contacts via Rabble.ca right now.

Right-Wing Mapping Collaboration

This project is on indefinite hold.

Natural Gas Collaboration

Earth Island Journal, Making Contact, LinkTV, Specialty Films, Chelsea Green and Care2 are pursuing a long-term collab on natural gas. They are at the LOI stage.