## logistics
Collateral to Make
Category | What Needs to be Done | Who can do it? | Printer Notes | Notes
Website | fix speakers page |  |  | Easy, no tech needed-- just time consuming
Display Posters | [choose posters to make]
| visual graphics from phillly meeting |  |  | Pick which 1-3 of the original graphics we should turn into posters
| original pocantico declaration | Jo Ellen |  | (located)
| poster w/ sponsor logos | Zoe, EIJ | 24x36 foamcore | Create a poster using logos
Reg Packets | [create content for packets]
| one-sheet describing TMC | Jo ellen | 1A color | revise one from last year | Done
| sponsor logos (same as poster) | Zoe, EIJ | 1B color
| one-sheet Info for attendees | Jo Ellen | 2A b/w | http://www.tmcmedia2016.org/hotel-info/ | Done
| one-sheet Info on Philly | MC | 2B b/w | nearby restaurants, bars, transit
| ballot for TMC member orgs | Linda Jue | 3AB, 4AB b/w | [nominating committee shd create this] | Done
| program-short version (1 page) | Jo Ellen | 5-6AB b/w | will pull from website | Done
| speaker bios | Jo Ellen |  | will pull from website
Name Tags | name tag list | Jo Ellen |  | will pull from online reg
| name tag design |  |  | design name tag using standard avery format: 74520
Post-Conf Email | thanks to sponsors | Jo Ellen
| evaluation form??? |  |  | should we do this in print or make it an after-conference survey?
Philly-based work to do
Printer/Copyshop | MediaCopy | Jo Ellen |  | Mary Beth: print@mediacopyonline.com
| Get everything printed/made | Jo Ellen
Office Depot/Staples | Folders for Reg Materials (150) | Jo Ellen
| Avery 74520 Name Tag Forms (175) | Jo Ellen
| tape to hold up posters | Jo Ellen |  | Needs to be special type that won't take off paint
| http://www.staples.com/ASTROBRIGHTS-Color-Paper-8-1-2-x-11-24-lb-5-Color-Happy-Assortment-500-sheets/product_507445 |  |  | one ream each
| http://www.staples.com/Mr-Sketch-reg-Scented-Watercolor-Marker-Chisel-Tip-Assorted-Colors-8-pk-20078TL-/product_833315 |  |  |  | 3x
http://www.staples.com/Sharpie-Electro-Pop-Limited-Edition-Ultra-Fine-Point-Permanent-Markers-Assorted-24-Pack-1927351-/product_569444
Costco | 2 cases white wine | Jo ellen
(assume 75-100) | 2 rounds brie | Jo ellen
| 3 other cheese (5-6 pounds) | Jo ellen
| 6 pounds crackers | Jo ellen
| 10 pounds prepared veggies | Jo ellen
| 3 quarts dip | Jo ellen
| 150 small plates | Jo ellen
| 150 plastic wine cups | Jo ellen
| cockatil napkins | Jo ellen
Philycam | Do they have serving materials? | Jo Ellen | yes | we need: cheese knives, corkscrew, cutting board for cheese, baskets for crackers