## Grant Budget
B-Word World Wide, Inc.
DishonorRoll Budget vs. Actual to Date
November 1, 2017 - June 15, 2018
|  |  | YTD Actual | Budget | $ Variance |  | % Variance | Notes
Revenue
|  | Project Funding from Media Consortium | 75000 | 75000 | 0 |  | 100%
Total Revenue |  |  | 75000 | 75000 | 0 |  | 100%
Expenses
| Project Management | DisHonorRoll Project Director | 10000 | 10000
|  | Media Watch Project Manager, Editor | 20992.43 | 24900 | -3907.57 |  | 84.31% | Many costs front loaded due to initial creation and
| Content Creation | Freelancers | 10150 | 10000 | 150 |  | 101.5% | All contracted and in process, but not all paid out yet - cash paymens to date = $2,825
|  | Investigative Journalism (Mother Jones) | 17500 | 17500 |  |  |  | includes travel
|  | Contractor/ resource guide | 2500 | 2500 | 0 |  | 100% | Completed
Marketing
|  | Social Media Campaign Director | 400 | 0 |  |  |  | Donated by Monica Cadena
|  | Video (negotiating to get this in kind from TYT) | 0 | 0 | 0 |  | 0% | Canceled--decided this was too expensive
|  | Photography (for Facebook) | 0 | 1200 | -1200 |  | 0% | Canceled- decided campaign would be better
|  |  | 200 |  |  |  |  | Landing Page on Bitch
|  | Facebook Boosts |  | 1200 | -1200 |  | 0% | Facebook Boosts
| Admin | Bookkeeping/Fiscal Sponsor Fees | 5250 | 5250
Total Expenses
|  |  | 66992.43 | 72550 | -6157.57 |  | 92.34% | At 8.5 months of a 12 month grant period our benchmark variance is 71%, so we are slightly ahead of budget, which is to be expected as many costs were front loaded
| contingency |  |  | 2450
Balance |  |  | 8007.57 | 0 |  |  |  | Editor (4000), freelancers (3000)