## Consortium projects
Project | Lead staff | Volunteer team | What's going on | Next steps | Rough costs
2008 election coverage | Steve, Tracy | Kathy Spillar/Ms., Clara Jeffery/Mother Jones, Don Hazen/Alternet, Ina Howard/New Press, Daffodil Altan/New America Media, Carol Jenkins/WMC, Chris Rabb/Afro-netizen, Martin Collier/Glaser Family Fund, David Michaelis/LinkTV, Julie Bergman Sender/Balcony FIlms, Cenk Uygur/Young Turks | Organize discussions with lead voter engagement groups and then congressional leadership on the role of the independent media in 2008 | Steve to contact Becky Bond/Working Assets, Tracy to contact Adam Green/MoveOn | TBD
Ad barter | Tracy | [Tracy can you fill this in?] | Ad barter group reconvening to work through next steps for web-only barter model. Tracy to contact CivicActions to talk about costs for platform build out | Conference call scheduled for 1PM Central, 1/16/07 | TBD
Book publishing | Steve | Tracy Van Slyke/ITT, Chris Rabb/Afro-Netizen, D.J. Francis/American Prospect, Alicia Daly/Ms., Jessica Clark/ITT, Kim Spencer/LinkTV, Tram Nguyen/Colorlines, Daffodil Altan/New America Media | Develop "co-op book review" idea - book review distributed to Consortium members. | Steve work with Ina to schedule discussion | TBD
Communications and PR | Steve | Cenk Uygur/Young Turks - to start | Steve and Cenk organizing description/proposal for PR project to serve interested Consortium members | Complete project proposal, organize conference call | $36,000 - $60,000
Consortium website | Steve | Tracy Van Slyke/ITT, Deanna Zandt | Steve and Deanna in discussion with CivicAction re alternatives to Drupal-only site (I.e., gathering existing online tools together for Consortium members) | Steve preparing memo for Deanna review and transmittal to CivicAction | $5,000 - $15,000
Ethnic-progressive media networking | Steve | Rinku Sen/Colorlines, Linda Jue/IPA, Tracy Van Slyke/ITT, Sandy Close/New America Media | Gauge interest in organizing follow up working meeting in conjunction with March 07 "Facing Race" conference in NYC. Build out specific ideas for colalboration/networking for funding opportunities and implementation. | Schedule call | TBD
Master list | Steve | Teresa Stack/The Nation, Jay Harris/Mother Jones, Tracy van Slyke/ITT, Alicia Daly/Ms. | Convene followup conference call to work out next steps with data (e.g., modeling/acquisition, privacy policy integration, develop marketing tools, etc). | Steve work with Teresa to schedule call. Recruit one more volunteer leader for the project | TBD
Mobile Media Project | Tracy | Joel Bleifuss/ITT, Ina Howard/New Press, Jason McKain/Free SpeechTV, Peter Leyden/NPI, Kathy Spillar/Ms., Lark Corbeil/PNS, Bonnie Boswell/RealTV, Sam Rosenfeld/American Prospect | Tracy to schedule conference call to shape out idea | Schedule call | TBD
Moving content to moving image media | Steve | To be organized | Meredith Blake leaving Participant Productions; Steve in touch to find out who replacement is. Steve has also contacted Cara Mertes at Sundance Documentary about meeting with Consortium members in early 2007 | Follow up calls, organize working group with video/tv Consortium folks
Opinion poll | Steve | Kathy Spillar/Ms., Paul Glastris/ The Washington Monthly, Kim Spencer/LinkTV, Sandy Close/New America Media, Rinku Sen/Colorlines, Katrina vanden Heuvel/The Nation, Chris Rabb/Afro-netizen, Jay Harris/Mother Jones | Steve to schedule conference call after New Year. Paul Glastris also put Danny Franklin of the Benenson Strategy Group in touch with Steve; Danny is preparing a proposal to the Consortium for a poll on "The State of the American Left" | Schedule call. Distribute Danny Franklin proposal to get the discussion going | $40,000 - $80,000
Tech camps | Deanna | NA | NYC Tech camp scheduled for 1/16/07. Announcement out, wiki set up. SF Tech camp date to be determined | Follow up email and calls | $2,500 - $5000
Washington DC reporter | Steve | Kathy Spillar/Ms., Joel Bliefuss and Tracy Van Slyke/ITT, Monika Bauerlein and Jay Harris/Mother Jones, possibly The Progressive and The Nation | Kathy and Steve scheduling time to talk and prepare project description | Get on the phone | $12,000 - $20,000
Web x-link | Steve | Tracy van Slyke/ITT, D.J. Francis/American Prospect, Ben Fuller/LinkTV | CivicActions to finish up design/UI, prepare documentation for users and administrator. Short term server location to be worked out | Steve in contact with CivicActions re completion of project | 3000