## Engineering Estimates
Project Estimates for the Mother Jones Media Consortium Advertisement Space Barter Project
Please note that these are only preliminary estimates – final estimates will depend on the exact requirements, interface and technical direction.
Basic Estimate | Hours | Details & Assumptions
Setting up basic website | 10
Installing modules | 5
Configuring/theming content types: |  | An average of 15 fields each
Organization | 5
Specs | 5
Print | 5
Online | 5
Audio | 5
Video | 5
Configuring/theming views:
Schedule listing | 10
Calendar listing | 10
Space finding/filtering | 10
Simple site theme | 20 | Customizing an existing Drupal theme
Tech Spec Writing | 25 | Variable based on choices in implementation options below
Total | 120
Notes: This would cover the very basics or recording the details for, finding and manually allocating ad. Space (i.e. A simple website with a database of entries listings)
E-mail reminders | Hours | Details & Assumptions
Manually e-mailing a contact person | 5 | User/e-mail specified on the Ad. space page
Manually e-mailing a group of people | 25 | Users/e-mails specified on the Organization page
Automatic e-mail notifications | 30 | E-mailing a message on (or a preset number of days before) a date field
Customized automatic e-mail notifications | 10 | The message sent can be customized in advance on a per-space basis
Total
Note: Individual or group functionality is a prerequisite for automated notifications
Audience/trade formula | Hours | Details & Assumptions
Conceive trade algorithm | 15 | Iterative work with Media Consortium to create workable algorithm for trades
Calculation based on ad. space fields | 5
Calculation based on Org. fields | 20 | See note
Calculation based on Spec. fields | 10-20 | See note
Allow override or manual addition/weighting | 5-15 | This would allow admins to deal with special cases (such as one org. helping another with the Ad. production)
Total | 20-75 | Total depends on the type of calculation needed for the trade algorithm
Note: This would involve fetching values from the Ad. space provider org (and/or their specs)., and including those in the calculation, along with fields from the Ad. itself.
“Pool” accounting | Hours | Details & Assumptions
Report listing transactions & balance for each Org | 20-50 | Depends on the level of detail required
Aggregate/summary report listing all Orgs. | 10-20 | Depends on the level of detail required
Total | 30-70 | Depends on the level of report detail agreed upon
Note: This is based on placing all ad. space into a 'pool'. Orgs get 'credit' for ad. space they provide, and 'debit' for space they use.
The 'currency' here is 'audience' (not dollars!) - this is similar to a local exchange trading scheme (LETS)
This is not a true account, it relies on 'social expectation' (possibly backed by rules) to ensure that Orgs don't get too in the 'red'
This system allows different donations of ad. space by different orgs. and for each ad. space to have different audience numbers
Accounting reports could cover either the current trading period, or 'all time' (or possibly both)
“Pool” allocation | Hours | Details & Assumptions
Manual allocation | 5 | A program admin manually allocates who gets each Ad space
Automatic allocation | 20-40 | All Ad. space that is currently unallocated is allocated according to one of the below algorithms
“Random” allocation | 20 | This is not truly random, because it would try and keep an overall balance of credit/debit for each Org.
“Shared” allocation | 20 | Unallocated spaces are 'shared out' (in descending audience order), rotating the org getting the 'top' space
“First-come” allocation | 10 | Orgs can choose an Ad. space as soon as that Ad. is in the system (or, all ads are in the system)
“Scarce” allocation | 30 | Artificial scarcity (making credit 'available for spending' at a slow rate, or making allocations happen in stages)
could help prevent the the same organizations always taking the 'highest value' ad spaces.
“Auction” allocation | 50 | Some kind of (normal, reverse, blind, dutch, etc) auction is used instead of the 'trade formula' to determine ad. space value
Total | 5-80 | Depends on the allocation type agreed upon
Note: There are obviously many different approaches here, and it should be possible to mix and match and extend this
Any of the approaches could be manually tweaked after the initial allocation
“Swap” accounting | Hours | Details & Assumptions
Swap listings/links | 15 | Listing matched swaps and linking between swapped space
Report listing swaps & audience reach for each Org | 35-60 | Depends on the level of detail required
Aggregate/summary report listing all Orgs. | 10-20 | Depends on the level of detail required
Total | 60-95 | Depends on the allocation type agreed upon
Note: In this context “swap” means that each allocation of 'A's ad. space to 'B' has a corresponding allocation of 'B's ad. space to 'A' (with an equal audience reach)
I think the 'swap' approach is more complicated from a technical and UI point of view than the “Pool” approach, especially as more features are added
These reports could only be feasibly and reliably generated if we had automated allocation (or allocation checking) to ensure swaps were valid
“Swap” allocation | Hours | Details & Assumptions
Manual allocation | 5 | A program admin manually allocates who gets each Ad space
Swap allocation checking | 20-35 | Ensuring that each ad. space use has an mutually returned use of equal audience
Automatic allocation | 70-200 | See note
Total | 95-240 | Depends on whether the swap allocation will be used
Note: We would need some approach where equivalent ad. spaces are automatically found and swapped, but with some element of both randomness and fairness
I find it difficult to conceive of a simple algorithm which could automate these swaps in a consistent way that is fair (over time) to each individual organization.
Trading groups | Hours | Details & Assumptions
“Soft” implementation | 10 | Used to help find ad. space relevant to you and as a forum for discussion
“Hard” implementation | 80-150 | Used as 'subsites' to restrict trades to a particular group and keep accounting and allocation for each group separate
Total | 90-160 | Depends on the use of groups, and the number of trade groups
Note: I think it would simpler overall to come up with a system that works for the group as a whole without needing trading groups
Permissions | Hours | Details & Assumptions
Users can create/allocate space for own org. only | 20 | Each user is only associated with a single organization
Multiple org users can update their org. and spec. pages | 30 | Each user is only associated with a single organization
Total | 50
Note: Drupal does not organize it's access control by groups, so this would need to be custom coded.
Without this functionality it would be an 'open system' – i.e. users would not be technically restricted to creating/updateing ad. space for their org. only
If we have 'trading groups' this could become more complex (since one of the simplest ways to do this would be to make each org. a group)
IA: Requirements 2.0 & Trade Structure | Hours | Assumptions
Clarify and revise open issues on individual requirements | 4-8 | MC (Tracy) to lead follow-up with stakeholders; Zoey to follow-up with CivicActions team
Gather more detail & finalize requirements |  | Tracy to lead this effort, plus meetings with Zoey to define key questions to ask, and to discuss impact of results.
Requirements specific to media types | 2-4
Requirements specific to schedules & distribution models | 2-4
Define governance structure | 1-4
Define business rules for trades | 1-4
Define exchange rate | 2-4
Define trade model | 4-8
Finalize phase designation, priority of requirements | 2-4 | Zoey to collaborate with Tracy, Owen, and CivicActions team
Create documentation for training and buy-in | 2-8 | Tracy and Zoey to revise conceptual model, if necessary. *This step is dependent on having buy-in from participants in the MC, and having defined stakeholders who can sign off on the model.
Total | 20-48
IA: Process Flows | Hours | Assumptions
Create process flows showing user paths, identify preliminary list of fields |  | Zoey and Tracy, with input from MC/CA team.
User enters organizational info & trade offerings | 4-5
User receives info on the exchange value of their offering (how much barter trade they get) | 4-5
User searches for ads their organization has offered and related deadlines | 4-5
User searches for ads their organization has received and related deadlines | 4-5
User looks at specs for an ad they've received | 4-5
Total | 20-25 | Process flow scope may be minimized if MC chooses a more minimal website for launch
IA: Wireframes | Hours | Assumptions
Finalize field and attribute list | 10 | Zoey to do any necessary follow-up with Owen; Tracy to do follow-up with MC Based on Tracy's findings from gathering requirements on diverse media types, define list of required fields and preliminary attribute list.
Page list, high-level sitemap | 12 | Zoey and Tracy Define list of pages on the sites; create high-level sitemap
Create wireframes for select priority pages. |  | Zoey and Tracy with feedback from CA/MC team. Note that wireframes for specific pages will only be created if required by tech team.
Input organization Info | 3-5
Input general ad specs | 3-5
Input ads offered | 3-5
View exchange value | 3-5
View trade received | 3-5
Calendar-general view | 3-5
Calendar-detail view | 3-5
Search | 3-5
Total | 46-62 | Process flow scope may be minimized if MC chooses a more minimal website for launch
System Administration | Hours | Details & Assumptions
SysAdmin | 10 | Set up of lists, hosts, trac, and other infrastructure. Does not include move to an offsite host.
Quality Assurance | Hours | Details & Assumptions
QA | 30-60 | Depends on functionality selected above
Project Management | Hours | Details & Assumptions
Project Management | 40-200 | Extremely variable based on choices in implementation and scope of project.

## Estimates Notes
NOTES ON ESTIMATES AND PROJECTIONS
MEDIA CONSORTIUM PROJECT INVOLVEMENT
Please note that these estimates are dependent on the Media Consortium members driving some of the tasks needed to complete this project. For example, I feel it would be vital for the Media Consortium to lead the conversations about the project governance structure. We feel that a high level of involvement is necessary to delivering a viable end-product. We recommend delegating a clearly defined, small group of stakeholders who --from the project start -- sign-off on milestones and deliverables.
TOTAL HOURS
Note that we have only listed CivicActions teams hours estimates in the hours column. Hours the Media Consortium puts in are not included- for each listed task/deliverable. This is particularly relevant for line items where Zoey has listed Tracy's involvement on IA tasks.
ESTIMATES RANGES
Where ever possible, we've listed hours ranges to accommodate the varied options for project build out. In our estimates, we can deliver a basic website, with ad entries listings in approximately 150 hours, or we can build the snazziest, fanciest, automated trade system around for upwards of 750 hours.
LETS SYSTEM – A SIMILAR TRADE MODEL
Here are some background links on LETS:
http://www.letslinkuk.net/home/theory.htm
http://en.wikipedia.org/wiki/LETS
http://www.gmlets.u-net.com/design/home.html
Here it is in 4 points:
People set up a club to trade between themselves, keeping their own record of accounts.
A directory of members' offers and requests—goods, services or items for hire, priced in local LETS units—is compiled and circulated.
Members use the directory to contact one another whenever they wish. They pay for any service or goods by writing a LETS cheque or credit note for an agreed amount of LETS units, or by exchanging printed LETS notes.
If applicable, the credit note is sent to the LETS bookkeeper who adjusts both members' accounts accordingly.
LETS is a fully fledged "monetary system", unlike direct barter, with LETS members able to earn credits from any member and spend them with anyone else on the scheme.