## Overview
Client: TMC
Date: 09/02/08
Project: Launch
Overview
Goals
Create awareness and buzz around new, issue-based media wires - Immigration, McCain, Healthcare
Generate traffic to Media wire sites (and ultimately back to TMC member sites) (target traffic - TBD)
Generate incremental users / readers to TMC member sites (via cross polination / new traffic)
Audience Segments
Users / readers interested in an independent journalistic pulse on key issues
Users / readers interested in one-stop shopping of these key issues
Members of the Press - keeping tabs on pulse of independent journalism community; providing steady stream of experts that can be contacted for media ops
Congress / Hill - keeping tabs on pulse of independed journalism community
Positioning
Users - The best of independent journalism online
Press - Top independent stories; authors that can be available to comment on timely issues
Congress / Hill - smart, independent thinking on issues key to voters / constituents

## Timeline
Client: TMC
Date: 09/02/08
Project: Launch
Launch Timeline
|  | Who | 2008-09-02 | 2008-09-03 | 2008-09-04 | 2008-09-05 | 2008-09-08 | 2008-09-09 | 2008-09-10 | 2008-09-11 | 2008-09-12 | 2008-09-15 | 2008-09-16 | 2008-09-17 | 2008-09-18 | 2008-09-19 | 2008-09-22 | 2008-09-23 | 2008-09-24
Newsladder Enhancements
| Set-up Newsladders to receive auto-feed of content | Caitlin | bar: 2008-09-04 to 2008-09-08
| Insert meta tags | Caitlin | bar: 2008-09-04 to 2008-09-08
| Google Ad Manager | Caitlin | bar: 2008-09-04 to 2008-09-08
Internal Outreach to TMC Members
| One on One Discussions | TMC | bar: 2008-09-10 to 2008-09-12
| - Widget distribution to TMC members (or links on TMC member sites) | TMC | bar: 2008-09-15
| - Remnant advertising space from TMC member sites (free at launch) | TMC | bar: 2008-09-15
| - TMC member sites feature TVS post / link to TMC press release | TMC | bar: 2008-09-16; 2008-09-18
| - Inclusion in TMC email efforts | TMC | bar: 2008-09-23
External Outreach
Email / Blogger List Research/Development
Target Audiences
| Congress Members | TMC/CS | bar: 2008-09-02 to 2008-09-05
| Communication Directors | TMC/CS | bar: 2008-09-02 to 2008-09-05
| Legislature Directors | TMC/CS | bar: 2008-09-02 to 2008-09-05
| Staff on Hill | TMC/CS | bar: 2008-09-02 to 2008-09-05
| Private List Serve | TMC/CS | bar: 2008-09-02 to 2008-09-05
| Members of Press | TMC/CS | bar: 2008-09-02 to 2008-09-05
| Media & Tech | ?
| Immigration Groups/Sites, Healthcare Groups / Sites | TMC
Blog Outreach
| Introduction & Widget | CS | bar: 2008-09-08 to 2008-09-09; 2008-09-15 to 2008-09-16
Target Audience TBD | bar: 2008-09-08 to 2008-09-09; 2008-09-15 to 2008-09-16
| Immigration group / sites outreach; healthcare groups / sites outreach | CS | bar: 2008-09-08 to 2008-09-09; 2008-09-15 to 2008-09-16
| Post | James | bar: 2008-09-08; 2008-09-11; 2008-09-17; 2008-09-22; 2008-09-24
Target Audience - All Segments
Huffington Post? What else
| Post | Max | bar: 2008-09-09; 2008-09-12; 2008-09-18; 2008-09-23 to 2008-09-24
Target Audience - All Segments
Huffington Post? What else
| Post | Tracy | bar: 2008-09-10; 2008-09-15; 2008-09-19; 2008-09-24
Target Audience - All Segments
Huffington Post? What else
Social Networks
Facebook
| TMC main page set-up | Max | bar: 2008-09-09
| Regular Content Updating | Tracy | bar: 2008-09-09
| Application Feed | Max | bar: 2008-09-09
| Twitter feed from each Newsladder | Max | bar: 2008-09-09
| Set up Facebook social ads | Max | bar: 2008-09-10 to 2008-09-23
PR
| Contact Represent | CS | bar: 2008-09-05
Minimum PR wireblast | bar: 2008-09-15
Schedule for PR Strategy - TBD | bar: 2008-09-15
Reporting
| Set-up Reporting Access for TMC | CS
| Development of Reporting Dashboard (weekly) | CS | bar: 2008-09-09
| TMC review / approval of Dashboard | TMC | bar: 2008-09-12
| Begin Delivery of Dashboard | CS | bar: 2008-09-16
Ongoing Timeline (TBD after Evaluation of Launch Strategy) | bar: 2008-09-02 to 2008-09-22
|  | Who | 2008-09-02 | 2008-09-03 | 2008-09-04 | 2008-09-05 | 2008-09-08 | 2008-09-09 | 2008-09-10 | 2008-09-11 | 2008-09-12 | 2008-09-15 | 2008-09-16 | 2008-09-17 | 2008-09-18 | 2008-09-19 | 2008-09-22 | 2008-09-23 | 2008-09-24
Blog Outreach
| Weekly Outreach - Top Stories | CS
Monthly Push of NewsLadder Widgets
Email Blast
| Target Audiences | TMC/CS | bar: 2008-09-04; 2008-09-11; 2008-09-18
| Readers/Contributors | TMC/CS | bar: 2008-09-09; 2008-09-16; 2008-09-23
| Congress Members | TMC/CS | bar: 2008-09-09; 2008-09-16; 2008-09-23
| Communication Directors | TMC/CS | bar: 2008-09-09; 2008-09-16; 2008-09-23
| Legislature Directors | TMC/CS | bar: 2008-09-09; 2008-09-16; 2008-09-23
| Staff on Hill | TMC/CS | bar: 2008-09-09; 2008-09-16; 2008-09-23
| Private List Serve | TMC/CS | bar: 2008-09-09; 2008-09-16; 2008-09-23
| Members of Press | ? | bar: 2008-09-09; 2008-09-16; 2008-09-23
| Media & Tech | TMC | bar: 2008-09-09; 2008-09-16; 2008-09-23
| Immigration Groups/Sites, Healthcare Groups / Sites | CS
Opportunistic Broadcast
| Air America | TBD
| Mario Solis Marich | James
| Dave Ross Show | James
| Blog Talk Radio | Max
| GRIT TV | TBD
| GoLeftTV | TBD
| Meet the Bloggers | TBD
| Other | TBD
Posting of content to existing NL Sites (Justice, OurTroops, Sustain, Iraq) |  | CS
Facebook Optimization |  | TMC
Green Agora
| Review program details / timing / launch plan | CS / TMC | 2008-09-02: TBD
| Define / Review TMC integration with site / Green NewsLadder | CS / TMC | 2008-09-02: TBD
| Establish TMC member open source accounts | CS | 2008-09-02: TBD
| Launch | CS | 2008-09-02: TBD
| Begin Content Posting | CS | 2008-09-02: TBD
| Begin Distribution / Outreach | CS | 2008-09-02: TBD
Online Advertising
| Paid Search (~$3000 from Sept 8 - Oct 31st) | CS
| Ongoing remnant advertising from TMC members (discount rate) | TMC
Subladder oppty - Common Sense can build up to 2 subladders per issue (Free) - for additional focus / targeting of issues
by region, issue, etc
Note on B12: Caitlin Doherty: Investigate Yahoo! Pipes
Note on B20: TVS: Honestly, don't know if they'll take a post from me. But if we can give them the basic wording to announce--that would be best. Either way, need to set deadline for getting this written and what we want to do
Note on B25: Caitlin Doherty: Different messaging, creative, call to action for each audience?
Note on B31: Caitlin Doherty: TH, Journolist, WIPT, WAM, PCN, Prog. Ex,PCN, Brownhouse, GET NAM to send to members???
Note on B33: Caitlin Doherty: Mashable, TechCrunch, Romenesko, NewsLeadership 3.0, E-Media Tidbits (Editor and Publisher)
Note on B39: TVS: Need help gathering lists?
Note on B41: TVS: Where are these posts going to be?
Note on C19: TVS: For how long? What does this mean?
Note on C20: TVS: MC staff need to do one-on-ones w/id'd MC members to get them onboard, answer tech questions, get the committed in advance so we can say we have MC members already committed and this is why this is going to ROCK!
Note on C37: TVS: Who do we want to target?
Note on C74: TVS: Who is the voice?