Outing the Corporations Editorial Collaboration

Project Overview

The Media Consortium is partnering with We the People to support special investigative coverage that tracks corporate influence on American politics. Reporting will be produced between September 19 and November 2, at the one-year mark ahead of the 2012 election. Throughout the development and production process, We The People will work with TMC members and allies to create a “media crescendo” moment—a moment when the stories produced by TMC members and the issue of corporate influence itself become a hot topic across all media—that can be used by advocacy groups and the netroots to create social action. In addition, We The People will feature TMC members’ stories as part of the high-profile live event it is planning for late fall.

Both TMC and WTP have a vital interest in reporting on corporate funding of elections in the wake of the Citizens United decision by the U.S. Supreme Court. The aim of this project is to facilitate such reporting and to increase its impact by a) contracting with a number of TMC members to produce such reports, b) managing the project such that all reports will appear within a limited period no longer than four weeks, and c) using a number of publicity vehicles including but not limited to social media to ensure the reports make a direct impact on the public.

Participants:

American Independent/Public News Service collaboration

Alternet

Free Speech TV

In These Times

Mother Jones

The Nation

Oakland Local/National Radio Project/Truthout collaboration

The Progressive

Yes! Magazine

Budget:

| Income |  |  |  |
| --- | --- | --- | --- |
|  | Release from 2010 Wyncote | $30,600 |  |
|  | Release from TMC General Support | $3,500 |  |
| Total |  | $34,100 |  |
| Expenses |  |  |  |
|  | TMC Staff: Erin Polgreen | $1,000 | 10% time for 2 months |
|  | We the People Staff: Tracy van Slyke | $0 | In Kind from WTP |
|  | Consultant: PR | $0 | In Kind from WTP |
|  | Consultant: Blogger | $1000 | TMC Blogger |
|  | Regrant to Members | $30,600 |  |
|  | Fiscal Sponsor Fee | $0 | Covered in first release |
|  | Overhead | $1,500 |  |
| Total |  | $34,100 |  |