## Sheet1
TMC 2010 Planning Grid | Lead Staff | Support | Overarching Goal(s) | Next Steps | Who | Deadline
Incubation/Innovation Lab | TVS | Jeanne/Andrew | Work with members to expand understanding of and implementation of game-changing technologies, tools and strategies. Goal is to encourage big thinking and set up experimentation that will take place in 2010 and 2011. | Digital Refresh |  | 2010-01-11
|  |  |  | Get drafts of applications for labs and consulting ready |  | 2010-02-10
|  |  | Focused on how this will help build lists and audiences, bring in new revenue, or expand their impact | Look at developing a handbook for R+D |  | late jan
|  |  |  | Start rolling out applications/explanations for small group labs | JB/TVS | mid-march
|  |  |  | What would it take to build/take on a lockin? | JB/TVS | Early April
|  |  |  | What would a micropayments campaign look like? | JB/TVS | Early April
MediaWire | Erin | Jeanne |  | Finishing tracking | EBP | End of March
|  |  |  | What are some goals to be out and about? | EBP/JB | End of March
|  |  |  | How to optimize reach/social networks | EBP/JB | End of March
|  |  |  | Talk about scaling project up to include listbuilding? | EBP | Late April
Independent Media Internship | Jeanne | Erin |  | Update 6 month schedule for interns | JB | Mid March
|  |  |  | Update language about internships | JB
Fundraising strategy
Proff dev calls
Update application process
Follow The Money | TVS | Jay | Working with members to develop editorial collaboration and impact around economic issues. Need to use this project to prove to funders and members the value of editorial collaboration | proposal in to arca, talked to panta rhea,
Membership (new and current) | Erin | ?? |  | gathering notes from membership convo
first big convo for new cc
|  |  |  | strategy for member engagement: newsletters? Conference calls? More staff writing? One on Ones? Erin to develop. | EBP
|  |  |  | erin will be implementing process and schedule how can we be active/transparent with members | EBP
|  |  |  | reconstituting the membership committee | EBP
Member List-Building | TVS | ????
We've done work to build and examine lists for print organizations, but how do we work to increase email lists? 1.) Building our own email list, maybe using the mediawire blogs to populate it.
Time sensitive
The Big Thaw roll-out | Erin/Jeanne? |  |  | Sending out hard copies
Organizing a conference call for members on some of big thaw topics. What will be useful/tangible to members? Bridge meeting and II Labs. How can this foster new ideas/be tangible enough to get people on the line.
publicity opportunities?
TMC Member Meeting | TVS | Erin/Jeanne |  | finalize agenda and recruit outside guests
publicity opportunities?
outreach to members and 1-1 harrassment
Get meeting notes/resources out to people and
Internal Organization
Fundraising | TVS | Bridget/??
|  |  |  | Individual donors/fundraising campaign | EBP/JB | May
Budget/Finances | TVS | Madeline