## Sheet1
Launch Plan - Draft
Overview
Goals
Create awareness and buzz around new, issue-based media wires - Immigration, McCain, Healthcare
Generate traffic to Media wire sites (and ultimately back to TMC member sites) (target traffic - TBD)
Generate incremental users / readers to TMC member sites (via cross polination / new traffic)
Audience Segments
Users / readers interested in an independent journalistic pulse on key issues
Users / readers interested in one-stop shopping of these key issues
Members of the Press - keeping tabs on pulse of independent journalism community; providing steady stream of experts that can be contacted for media ops
Congress / Hill - keeping tabs on pulse of independed journalism community
Positioning
Users - The best of independent journalism online
Press - Top independent stories; authors that can be available to comment on timely issues
Congress / Hill - smart, independent thinking on issues key to voters / constituents
Timing
Lay the foundation now - 9/3
'TMC' Launch on the Wednesday after Labor Day (9/3) (to TMC community)
What does this consist of? Need to detail out...
'Hard' launch on Monday 9/8 (after RNC convention)
Tactics
|  |  | Timing | 2008-08-17 | 2008-08-24 | 2008-08-31 | 2008-09-07 | 2008-09-14 | 2008-09-21 | 2008-09-28 | 2008-10-05 | 2008-10-12 | 2008-10-19 | 2008-10-26
Site
Launch Healthcare | bar: 2008-08-17 to 2008-08-31
Launch Immigration | bar: 2008-08-17 to 2008-08-31
Complete TMC-specific widget | bar: 2008-08-17 to 2008-08-31
Outreach (internal - TMC members)
Widget distribution to TMC members (or links on TMC member sites)
Remnant advertising space from TMC member sites (free at launch)
For how long? What does this mean?
All TMC member sites feature TVS post / link to TMC press release
Honestly, don't know if they'll take a post from me. But if we can give them the basic wording to announce--that would be best. Either way, need to set deadline for getting this written and what we want to do | bar: 2008-08-31
MC staff need to do one-on-ones w/id'd MC members to get them onboard, answer tech questions, get the committed in advance so we can say we have MC members already committed and this is why this is going to ROCK!
Inclusion in TMC email efforts
Other
Outreach (external)
| Launch - James Post |  |  | 2008-08-24: Where?
| Launch - Max Post |  |  | 2008-08-24: Where?
| Launch - Tracy Post |  |  | 2008-08-24: Where?
| Launch - Congress mbrs / staff on hill |  |  | 2008-08-24: Get Com. Directors, Leg. Directors, who else???
| Launch - Private List Serve |  |  | 2008-08-24: TH, Journolist, WIPT, WAM, PCN, Prog. Ex,; 2008-08-31: PCN, Brownhouse, GET NAM to send to members???
Launch - Members of Press (gather list, include in weekly NL email)
Ongoing - Blog outreach - introduction & widget
Who do we want to target
Ongoing - Immigration group / sites outreach; healthcare groups / sites outreach
Need Help gathering lists?
Ongoing - Members of Press - Weekly email (top stories)
Ongoing - Top Blogs - Weekly outreach - top stories (who is the voice?)
Media and Tech lists? Mashable, TechCrunch, Romenesko, NewsLeadership 3.0, E-Media Tidbits (Editor and Publisher)
Broadcast
Air America
Mario Solis Marich (James)
Dave Ross Show (James)
Blog Talk Radio
GRIT TV? GoLeftTV? Meet the Bloggers?
Other
PR
Work with (Represent, Inc) to develop launch strategy
- minimum PR wireblast
Social Networks
Facebook - TMC main page set-up
Facebook - Content updating (McCain / TMC)
Application Feed
Twitter feed from each Newsladder
Email
Weekly Newladder email
Online Advertising
Paid Search (~$3000 from Sept 8 - Oct 31st)
Ongoing remnant advertising from TMC members (discount rate)
Subladder oppty - Common Sense can build up to 2 subladders per issue (Free) - for additional focus / targeting of issues
by region, issue, etc