Developing Timeline
January

- working on development, partners, timelines of II Labs

Jan 7/8

- TVS starts draft of applications for both one-on-one consulting and small group labs

Jan 10/11--Golis meets w/TMC staff in Chicago--II LAB development

- Review/Update draft applications for II Lab components

- Identify criteria for acceptance to one-one-on timeline

- Template timeline/hours per organization over 3 months and start dates

- Create template agenda for 2-day retreat for one-on-one consulting

  - Create draft of advanced questionairre b4 retreat

AGENDA
1) Review/Finalize goals and projected outcomes for II Lab: one-on-one consulting. (Can we think of a better name for this?)
2) Review overall timeline over next few months and adjust as needed
3) Determine capacity (number of orgs) and timing (when to start, how many at a time, how man hours per org/month)
4) Draft application forms for members and description of project
5) IF TIME: draft out template agenda for 2-day strategy retreat with orgs
6) Next Steps

Jan. 18-22

- TVS finalize research partner for small-group labs

- Sketch out (with small group of advisers?) on template schedule for small group labs

Process Questions to determine

- How many min. and max. orgs in small group labs?

- How many small group labs can a member be in during 12 months (are we in danger of people wanting to be in all 3?)

- What are requirements for participation?

- Template agenda for in-person meetings to brainstorm/develop

- Should we have groups apply for before each lab or apply at beginning and slot them in throughout year?

- Need a MOA for all groups in II Lab? (agreements of participation, public sharing of certain info, etc...)

February

- Continue development/finalization of all plans (see below) throughout Feb.

Feb 1-5

- Send out explanation/applications to members

Feb. 25-26-MC meeting

- In-person explanation/review of II Lab at meeting

- Conversations/Panels part of shaping II Lab focus

March 5
Deadline for II Lab applications

March 5-11
Review applications/decide who to take on

March 15
Announce to individual members who's in for one-on-one consulting, start dates and important dates

April 1
Start!?!?



Preparation
Recruiting Members
Application process finished 2 weeks after member meeting? Kick off in late April?
One-on-one convos with members leading up to it

Announcement emails
Applications

- one-on-one consulting

- small group participation

- (requirements, org needs, deadline for turning in, etc..)

Apps Must include:

- Impact goals

- Mini-Digital profile

- Commitment agreement (staff/$)

- What are questions/queries?

Small-group labs

- Same as above

- rating system of what lab to be in?

Timelines

- Timeline leading up to launch (applications developed/done/out/deadlines,

- Template timeline for one-on-one consulting (retreat prep and implementation, list of expected goals/outcomes per month, etc..)

- Template timeline for small group labs (start, implement phases, list of expected goals/outcomes per month, in-person meeting)

Extra Staffing needs
Golis stipend/hours
Researcher/Synthesizer?  Partner with University? Other partners like CJR? Hire grad student??

Process Questions to determine

- How many min. and max. orgs in small group labs?

- How many small group labs can a member be in during 12 months (are we in danger of people wanting to be in all 3?)

- What are requirements for participation?

- Template agenda for in-person meetings to brainstorm/develop

- Should we have groups apply for before each lab or apply at beginning and we will tell them which one they are in?

Discuss w/Golis
Timeline for next steps/roll out
How many groups take on for first 3-6 months?  Want to start 3 weeks apart from each other? 
Application develop--what should be in it?  What do we need to know from them?
Start outlining process a bit more: each month will look like...