## Schedule
Support Your Media, TMC Collaborative Fundraiser, February 15, 2012
Live Production Date 2/9/12; Air date 2/15/12
OBJECTIVES | DELEGATION | DEADLINE | TIMELINE
Production Dates Set | All | 2012-01-15 | 31 days out
Program Grid Schedule Draft (w/Dev.) | Jo Ellen | 2012-01-20 | 25 days out
Program Selection Draft | Steve, Louise, Eric, Jo Ellen | 2012-01-25 | 20 days out
Final Program Selection | Steve, Louise, Eric, Jo Ellen | 2012-01-25 | 20 days out
Promo and Bumpers Scripts Due | Jo Ellen | 2012-02-01 | `14 days out
License rights checked, re-license if needed | n/a | n/a | n/a
Recruit/Hire Crew | Alexander | 2012-01-25 | 20 days out
Contracts & Tapes Due in House | Jo Ellen | 2012-02-01 | 14 days out
Crew in house, Laura in house, taping | Jo Ellen | 2012-02-09 | 6 days out
Promo and Bumpers Shoot | All | 2012-02-09 | 6 days out
Interview Shoot | All | 2012-02-09 | 6 days out
Create Livestream Storyboard | Eric/Jo Ellen | 2012-02-10 | 5 days out
Promo Production Complete | Jo Ellen | 2012-02-11 | 4 days out
Program Schedule Final in Livestream Storyboard(w/Dev.) | Teo/Colleen/Rob | 2012-02-11 | 4 days out
Programs Segments trimmed in Final cut pro timeline | Lauren/Alexander//Marcy/Antoinette | 2012-02-11 | 4 days out
Program Elements Uploaded into Livestream as Storyboard element | Lauren | 2012-02-13 | 2 days out
Storyboard Ready for Live Day | Teo | 2012-02-13 | 2 days out
Confirmed FTP Files on Server | Lauren | 2012-02-13 | 2 days out

## Taping Schedule 2-9
2/9 FSTV Taping Day | Taping Schedule
9:00 |  | Jo Ellen arrives
9:30 |  | Engineers arrive/ equipment test
10:00 |  | Crew, Laura arrive/ review of day
10:30 |  | Tech rehearsal
11:00 | 1
11:15 | 2
11:30 | 3
11:45 | 4
12:00 | 5
12:15 | 6
12:30 |  | LUNCH
1:30 | 7
1:45 | 8
2:00 | 9
2:15 | 10
2:30 | 11
2:45 | 12
3:00 |  | BREAK
3:30 | 13
3:45 | 14
4:00 | 15
4:15 |  | Laura Pitch (support your media)
4:30 |  | Jo Ellen (Golden Ticket)
4:45 |  | Jo Ellen (support your media)
5:30 |  | WRAP

## Booking
Interest? | Outlet | Reporter | Pitch
| Truthout | Jason Leopold
| Yes! Magazine | Sarah van Gelder | Occupy Movement book; Curbing Corporate Power--mag coming out Feb 20;